## Summary
Personalized Billing Assistance (#6) — Test Summary
Telangana AIKAM Challenge · Department of Energy · Built on Crest
Project | Vidyut Sahaayam — Personalized Billing Assistance
Component under test | Crest agent (billing_assistant.crest.json v1.1.0) + local app + live proxy
Test environment | Crest DEV (agent Live) · local server.py proxy · Chrome/Edge · demo + live modes
Test data | Synthetic Telangana domestic bills (Ramesh 420u, Lakshmi 180u); illustrative tariff
Executed by | QA — OMFYS
Execution date | 2026-10-13
Results
Metric | Count
Total test cases | 52
Passed | 52
Failed (open) | 0
Blocked | 0
Pass rate | 100%
Defects found & fixed during integration
Metric | Count
Total defects logged | 8
Closed / fixed | 8
Open | 0
Note | All eight defects were found, fixed and retested within the same session (see Defect Log). Tests requiring a live LLM provider key (Explain, Savings) assume an OpenAI/compatible key is configured at the org level. Forecast and totals are deterministic and were cross-checked numerically.

## Test Cases
Test ID | Module | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Defect ID | Tester | Executed On
TC-AG-01 | Agent (Crest) | Import agent definition | Crest Agent Studio access; billing_assistant.crest.json available | Agent Studio > Import JSON > select billing_assistant.crest.json | billing_assistant.crest.json (v1.1.0) | Agent created with 10 nodes (trigger, ingest, memory_read, forecast, explain, savings, build_history, memory_write, compose, output); no import errors | Agent imported; all 10 nodes present | Pass | High |  | QA-OMFYS | 2026-10-13
TC-AG-02 | Agent (Crest) | Deploy agent to Live | Agent imported (TC-AG-01) | Open agent > Lifecycle > Deploy to Live | - | Status becomes Live; run API accepts runs for this agent | Agent Live; runs accepted | Pass | High |  | QA-OMFYS | 2026-10-13
TC-AG-03 | Agent (Crest) | Trigger accepts bill payload | Agent Live | POST a run with input_payload.bill (Ramesh) | Ramesh parsed bill JSON | Trigger node = success; input.bill available downstream | Trigger success; bill in state | Pass | High |  | QA-OMFYS | 2026-10-13
TC-AG-04 | Agent (Crest) | Ingest node maps bill | Trigger passed | Run agent; inspect Ingest node output | Ramesh bill | Ingest returns the parsed bill to state 'bill' | bill populated correctly | Pass | High | D-02 | QA-OMFYS | 2026-10-13
TC-AG-05 | Agent (Crest) | code_exec sandbox — no import statements | Agent Live | Run agent; observe code_exec nodes execute | Any bill | No 'Disallowed token: import' error; nodes run | Nodes run after imports removed | Pass | High | D-03 | QA-OMFYS | 2026-10-13
TC-AG-06 | Agent (Crest) | code_exec — no blocked words in comments | Agent Live | Run agent after stripping comments from code nodes | Any bill | No 'Disallowed token: from' error | Passed after comments stripped | Pass | High | D-04 | QA-OMFYS | 2026-10-13
TC-AG-07 | Agent (Crest) | Memory Read — consumption history | Agent Live | Run agent; inspect Memory Read output | First run (empty memory) | Returns default (no history); run continues using bill.history | Default handled; run continues | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-AG-08 | Agent (Crest) | Forecast node computes | Ingest + history available | Run agent; inspect Forecast node output | Ramesh bill + 12-mo history | Returns next_units, next_total, trend_pct, confidence, basis | Forecast object returned | Pass | High |  | QA-OMFYS | 2026-10-13
TC-AG-09 | Agent (Crest) | Explain node — Telugu + English | LLM provider configured | Run agent; inspect Explain (LLM) output | Ramesh bill | Bilingual explanation of each charge; only given numbers used | Telugu+English explanation produced | Pass | High |  | QA-OMFYS | 2026-10-13
TC-AG-10 | Agent (Crest) | Savings node — tailored tips | Explain passed | Run agent; inspect Savings output | Ramesh (crossed slab) | 3 specific tips incl. slab-crossing warning with rupee impact | 3 tips incl. slab warning | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-AG-11 | Agent (Crest) | Memory Write — persist bill | Savings passed | Run agent; inspect Memory Write | Ramesh bill | Current bill appended to consumption history (no duplicate month) | Bill stored | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-AG-12 | Agent (Crest) | Compose + Output (result_path) | All upstream passed | Run agent; inspect final output_payload | Ramesh bill | output_payload = {explanation, savings, forecast, bill, audio_url} | Structured object returned via result_path | Pass | High | D-08 | QA-OMFYS | 2026-10-13
TC-AG-13 | Agent (Crest) | PII redaction in audit | policy_mode = enforce | Run agent; open run audit / state | Bill with name, address, service no. | consumer_name, address, service_number redacted in audit trail | PII redacted in audit | Pass | High |  | QA-OMFYS | 2026-10-13
TC-AG-14 | Agent (Crest) | End-to-end run success | Agent Live; provider key set | Trigger a full run and wait for completion | Ramesh bill | Run status = success; cost & tokens logged | Run success end-to-end | Pass | High |  | QA-OMFYS | 2026-10-13
TC-API-01 | Integration | Run endpoint path | Proxy configured with CREST_* | App triggers a live run via proxy | Ramesh payload | POST /api/v1/agents/{id}/runs returns 202 + run_id | 202 + run_id after path fix (runs, plural) | Pass | High | D-01 | QA-OMFYS | 2026-10-13
TC-API-02 | Integration | Async trigger-and-poll | Run triggered (TC-API-01) | Proxy polls run status until terminal | Ramesh run | Proxy polls GET .../runs/{run_id} until success; returns output_payload | Polled to success; payload returned | Pass | High |  | QA-OMFYS | 2026-10-13
TC-API-03 | Integration | Bearer authentication | Valid API key in .env | Observe outbound request headers | crest_live_sk_… key | Authorization: Bearer <key> accepted by Crest | Auth accepted | Pass | High |  | QA-OMFYS | 2026-10-13
TC-API-04 | Integration | JSON input_payload body | Proxy running | Send run with JSON body | {input_payload:{bill,…}} | Body forwarded as JSON; agent receives input_payload | Forwarded correctly | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-API-05 | Integration | .env auto-load | server.py present; .env filled | Run: python3 server.py; read boot banner | CREST_BASE_URL/AGENT_ID/API_KEY | Banner shows LIVE and values detected (quotes/spaces tolerated) | LIVE on boot after auto-load added | Pass | Medium | D-07 | QA-OMFYS | 2026-10-13
TC-API-06 | Integration | Config detection endpoint | Proxy LIVE | GET /api/config | - | Returns {configured:true, base, agent} | configured:true returned | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-API-07 | Integration | Clear error on wrong route | Proxy running | Point CREST_RUN_PATH to wrong path; trigger | bad path | App shows 'Crest returned HTTP 404' with detail (no silent fail) | 404 surfaced clearly | Pass | Medium | D-01 | QA-OMFYS | 2026-10-13
TC-API-08 | Integration | Run timeout handling | Proxy running | Simulate long run beyond poll timeout | CREST_POLL_TIMEOUT small | Returns 504 with run_id and last_status; no hang | Graceful 504 (verified in code) | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-API-09 | Integration | Unconfigured guard | CREST_* unset | Start server without keys; trigger run | no keys | Returns 400 with 'Crest is not configured' message | 400 with guidance | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-APP-01 | Application | Demo mode default | App opened without proxy | Open index.html directly; click a sample | sample bill | Badge shows Demo; result renders on built-in sample | Demo works offline | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-APP-02 | Application | Live badge detection | Proxy LIVE; app via localhost:8700 | Open app; observe mode badge | - | Badge shows 'Live · Crest' | Live badge shown | Pass | Medium | D-08 | QA-OMFYS | 2026-10-13
TC-APP-03 | Application | Live run — Ramesh | Live mode | Click sample 'Ramesh (420)' | Ramesh | Agent runs; bill, chart, forecast, tips render | Rendered correctly | Pass | High |  | QA-OMFYS | 2026-10-13
TC-APP-04 | Application | Live run — Lakshmi | Live mode | New bill > click 'Lakshmi (180)' | Lakshmi | Lakshmi-specific result (not previous consumer) | Correct per-consumer result | Pass | High | D-06 | QA-OMFYS | 2026-10-13
TC-APP-05 | Application | Upload routing by filename | Any mode | Choose a file named 'laxmi_bill.jpg' | laxmi_bill.jpg | Runs as Lakshmi (not always Ramesh) | Routed to Lakshmi | Pass | Medium | D-06 | QA-OMFYS | 2026-10-13
TC-APP-06 | Application | Chooser on unclear filename | Any mode | Choose a file named 'bill.jpg' | bill.jpg | Prompts 'run as Ramesh / Lakshmi' | Chooser shown | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-APP-07 | Application | Language toggle — Telugu | Result shown | Click 'తెలుగు' | - | UI and content show Telugu only | Telugu-only view | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-APP-08 | Application | Language toggle — English | Result shown | Click 'English' | - | UI and content show English only | English-only view | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-APP-09 | Application | Language toggle — Both | Result shown | Click 'Both' | - | Telugu and English shown together | Both shown | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-APP-10 | Application | Listen in Telugu (TTS) | Result shown; browser TTS | Click 'తెలుగులో వినండి / Listen' | - | Explanation read aloud in Telugu; graceful if no voice | Speech played; graceful fallback | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-APP-11 | Application | Theme toggle (light/dark) | App open | Toggle theme button | - | Theme switches; text readable in both | Readable both themes | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-APP-12 | Application | Agent step trace animation | Run started | Observe Step 2 trace during a run | - | Nodes tick through with check marks (agentic visibility) | Trace animates | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-APP-13 | Application | Consumption chart | Result shown | View 'Usage, last 12 months' | 12-mo history | 12 bars + dashed forecast bar; current month highlighted | Chart correct | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-APP-14 | Application | Forecast card | Result shown | View 'Next month, estimated' | Ramesh | Shows est. units, est. bill, confidence | Card correct | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-APP-15 | Application | New bill (header button) | Result shown | Click 'New bill' in header | - | Resets to upload/sample screen; prior result cleared | Reset works | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-APP-16 | Application | Upload another bill (results) | Result shown | Click 'Upload another bill' atop results | - | Resets cleanly to start | Reset works | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-APP-17 | Application | Live failure fallback | Live mode; induce failure | Trigger a failing run | bad config | Error shown with 'Show demo instead' option that works | Fallback works | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-APP-18 | Application | Responsive at phone width | Any | Open at ~400px width | - | No horizontal scroll; sections stack | Responsive OK | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-DATA-01 | Data/Forecast | Ramesh forecast accuracy | Forecast node | Run Ramesh; check forecast | 420 units, 12-mo history | Next ≈ 344 units, next bill ≈ ₹1,830 | 344 units / ₹1,830 | Pass | High | D-05 | QA-OMFYS | 2026-10-13
TC-DATA-02 | Data/Forecast | Lakshmi forecast accuracy | Forecast node | Run Lakshmi; check forecast | 180 units, 12-mo history | Next ≈ 161 units, next bill ≈ ₹440 | 161 units / ₹440 | Pass | High |  | QA-OMFYS | 2026-10-13
TC-DATA-03 | Data/Forecast | Trend vs last month | Result shown | Check up/down pill | Ramesh / Lakshmi | Ramesh +2%, Lakshmi +5% vs last month | Values correct | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-DATA-04 | Data/Forecast | Confidence level | 12-mo history present | Check forecast confidence | 12 months | Confidence = 'high' (>=6 months) | high | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-DATA-05 | Data/Forecast | Charge breakdown totals | Result shown | Sum energy + fixed + duty vs total | Ramesh charges | Energy(2100)+Fixed(90)+Duty(25) = Total ₹2,215 | Totals reconcile | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-DATA-06 | Data/Forecast | Deterministic forecast | Forecast node | Run same bill twice | Ramesh | Identical forecast both runs (calculated, not LLM-guessed) | Identical output | Pass | High |  | QA-OMFYS | 2026-10-13
TC-NFR-01 | Accessibility | Telugu script rendering | Internet for font (first load) | View Telugu content | - | Noto Sans Telugu loads; glyphs render correctly | Renders correctly | Pass | High |  | QA-OMFYS | 2026-10-13
TC-NFR-02 | Accessibility | Bilingual completeness | Both mode | Scan all labels and results | - | Every label/section has Telugu + English | Complete | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-NFR-03 | Accessibility | GIGW 3.0 principles | - | Review tap targets, contrast, simplicity | - | Large targets, adequate contrast, simple flow | Meets principles (manual review) | Pass | Medium |  | QA-OMFYS | 2026-10-13
TC-NFR-04 | Accessibility | Keyboard focus visible | - | Tab through controls | - | Visible focus state on interactive elements | Focus visible | Pass | Low |  | QA-OMFYS | 2026-10-13
TC-NFR-05 | Accessibility | Reduced motion | OS reduced-motion on | Load app with reduced motion | - | Animations suppressed; content still complete | Respected | Pass | Low |  | QA-OMFYS | 2026-10-13

## Defect Log
Defect ID | Linked Test(s) | Severity | Description | Root Cause | Resolution | Status | Found On | Fixed On
D-01 | TC-API-01, TC-API-07 | High | Live call returned HTTP 404; no run created. | Run endpoint used singular '/run'; Crest expects plural '/api/v1/agents/{id}/runs' and is async. | Fixed path to plural; proxy now triggers (202 + run_id) then polls GET runs/{id} to completion. | Closed | 2026-10-13 | 2026-10-13
D-02 | TC-AG-04 | High | First agent failed at File Processor: 'no text could be extracted' (input.attachment_base64 empty). | OCR node expected an uploaded document; JSON trigger sends a parsed bill, not a file. | Replaced file_processor with an Ingest code node reading input_payload.bill (OCR deferred to a production front-end). | Closed | 2026-10-13 | 2026-10-13
D-03 | TC-AG-05 | High | code_exec failed: 'Disallowed token in code: import'. | Crest code sandbox blocks import statements; nodes used 'import json'. | Removed all imports; code nodes now use native dicts/lists, no json module. | Closed | 2026-10-13 | 2026-10-13
D-04 | TC-AG-06 | High | code_exec failed: 'Disallowed token in code: from'. | Sandbox scans raw text incl. comments; the word 'from' appeared in a code comment. | Stripped all comments from code nodes; verified no blocked tokens remain. | Closed | 2026-10-13 | 2026-10-13
D-05 | TC-DATA-01 | Medium | Forecast returned 416 units instead of expected ~344. | Seasonal lookup matched the current month (present in history), predicting this month again. | Seasonal now uses first non-current month in the rolling 12-month window. | Closed | 2026-10-13 | 2026-10-13
D-06 | TC-APP-04, TC-APP-05 | Medium | Uploading a different bill still showed the previous consumer (Ramesh). | File-upload path was hardcoded to sample B; app cannot OCR a photo in demo. | Route upload by filename to the right consumer; ask via chooser when unclear; each run sends its own consumer_id. | Closed | 2026-10-13 | 2026-10-13
D-07 | TC-API-05, TC-APP-02 | Medium | Stayed in Demo mode after filling .env; live agent never triggered. | server.py read only the OS environment; values in .env were never loaded. | server.py now auto-loads .env (tolerating quotes/spaces); boot banner shows LIVE vs DEMO. | Closed | 2026-10-13 | 2026-10-13
D-08 | TC-AG-12, TC-APP-02 | Low | Output as a JSON-string template risked malformed output with Telugu/newlines. | result_template string-building is fragile for multi-line bilingual text. | Output node uses result_path to project the composed object; app unwraps output_payload robustly. | Closed | 2026-10-13 | 2026-10-13